## Setup and context links
Enter Stakeholder Group Name in cell A2:
MIC Special Session on DER
Enter issue title (use title from Issue Tracking if applicable) in cell A5:
Distributed Resources in PJM Markets
Link to Problem Statement
http://www.pjm.com/~/media/committees-groups/committees/mrc/20160526/20160526-item-10-distributed-battery-storage-problem-statment-proposed-revision.ashx
Link to Issue Charge
http://www.pjm.com/~/media/committees-groups/committees/mrc/20160418-special/20160418-item-02a-distributed-battery-storage-issue-charge-revised-1,-d-,28,-d-,16-clean.ashx
Link to IssueTracking
http://www.pjm.com/committees-and-groups/issue-tracking/issue-tracking-details.aspx?Issue={FCADF6DC-FA84-4F5E-9B33-DE2428F47A2B}

## WORK PLAN 2017
MIC SPECIAL SESSION ON DER
Updated: January 26, 2017
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC | [5 empty] | 2012-11-29
üVote at MRC | [6 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  |  | 2013-03-01: 2013-03-01
[11 empty] | Phase I - Ancillary Services | [7 empty] | Phase II - Capacity | Phase III - Energy
Detailed Work Plan | 6.26 | 7.17 | 7.31 | 8.9 | 8.26 | 8.28 | 9.9 | 9.18 | 9.24 | 9.26 (MRC) | Special MRC 6.17.16 | Special MRC 8.24.16 | Special MRC 10.12.16 | Special MIC 12.16.16 | Special MIC 2.01.17 | Special MIC 3.02.17 | Special MIC 4.10.17 | Special MIC 5.01.17
Create Charter |  | x | x | x | bar: 2012-11-01 to 2012-12-01
Provide Education |  |  | x | [7 empty] | x | x | x | x | x
Document Interests |  |  |  | x | [9 empty] | x | bar: 2012-11-01 to 2012-12-01
Develop & Refine Design Components | [13 empty] | x | x | x | bar: 2012-11-01 to 2012-12-01; 2013-02-01
Develop & Refine Component Options | [14 empty] | x | x | x | x
Develop & Refine Solution Packages | [16 empty] | x | x
Build Consensus | [17 empty] | x
MIC Vote

## 1. Interest Identification
MIC Special Session on DER
Distributed Resources in PJM Markets
Interest Identification
| Category | Interests
1 | Access to Markets / Barrier Removal | Fair and open access to markets
2 | Access to Markets / Barrier Removal | Design components to address issues with DER retail customer participation in any PJM wholesale market, e.g., interconnection studies, requirements, etc., should reflect an appropriate size threshold that would exclude individual retail customers with non-significant loads, e.g., less than 100kW, unless included in an aggregation.
3 | Access to Markets / Barrier Removal | Participation in any PJM wholesale market should only be the result of a voluntary and/or affirmative choice of each participating individual retail customer.
4 | Access to Markets / Barrier Removal | DERs can participate in all PJM markets to the limits of their technical capability.
5 | Access to Markets / Barrier Removal | Clear, non-discriminatory rules for determining energy and capacity injection rights.
6 | Access to Markets / Barrier Removal | Support for the widest possible variety of ownership arrangements.
7 | Access to Markets / Barrier Removal | Clear and efficient processes and requirements for resources to enter PJM markets.
8 | Grid Ops | Safe and reliable operations of grid
9 | Grid Ops | Efficient use of assets
10 | Grid Ops | Blindly dispatching resources without seeing all constraints should be carefully considered as it could impact system reliability and safety.
11 | Grid Ops | Visibility of system constraints and coordination around them is critical to bulk transmission dispatch and it should not be ignored when dispatching resources on the distributions system.
12 | Grid Ops | Many distribution companies are currently evaluating the benefits/cost of grid modernization with their respective state regulators. Regional differences should be respected as close coordination between entities is required to ensure the delivery of safe and reliable electricity.
13 | Jurisdiction of DER | Any results from this stakeholder process should not interfere or alter the jurisdictional authority of state or local regulatory commissions over individual retail customers and/or their transactions with public utilities that are regulated by a state or local jurisdictional regulatory authority.
14 | Jurisdiction of DER | Any FERC–state/local regulatory conflicts arising from any results from this stakeholder process must be resolved before implementation.
15 | Jurisdiction of DER | Any results from this stakeholder process should not interfere or alter the privacy of retail customers as customers of public utilities regulated by a state or local regulatory authority.
16 | Jurisdiction of DER | Participation should be subject to relevant state or local rules and regulations.
17 | Jurisdiction of DER | PJM rules limited to enforcing wholesale market provisions while coordinating with non-wholesale state laws and regulations.
18 | Jurisdiction of DER | Clear delineation between EDC and PJM responsibilities in whatever rules are developed.
19 | Jurisdiction of DER | DER must observe all jurisdictional boundaries including interconnection standards.
20 | Market Rules & Req's | Framework that is capable of working with future market products.
21 | Market Rules & Req's | Comparable requirements and obligations of DER to existing supply-side generation and storage.
22 | Market Rules & Req's | Rules made with awareness of open FERC DER NOPR: https://www.ferc.gov/whats-new/comm-meet/2016/111716/E-1.pdf
23 | Market Rules & Req's | Administrative simplicity.
24 | Market Rules & Req's | Resources should be rewarded for their value (and costs) to the system which requires dispatch incentive tied to local constraints. Resources should be compensated for services they provide to the grid. Conversely, if resources consume grid services, they should pay for services consumed.
25 | Miscellaneous | Agree on a consistent definition of DER
26 | Settlements / Accounting | Appropriate accounting
27 | Settlements / Accounting | Design components to implement aggregation should rely on metered versus estimated values of service(s) provided.
28 | Settlements / Accounting | Capturing retail end-use kWh for proper retail energy accounting.

## 2. Options Matrix- Design Comp.
MIC Special Session on DER--Distributed Resources in PJM Markets--OPTIONS MATRIX
Solution Options2
# | Design Components1 Problem Scope: DER behind a customer load meter providing Ancillary Services | Priority | Status Quo DR | Status Quo front-of-meter "Buy-all/Sell-all": dedicated service drop to DER | Status Quo front-of-meter "Sell excess": DER wired with load behind metering | A | B | C | D | E
*
1 | Interconnection process requirement for injections/export beyond the POI to the distribution or transmission system for participation in PJM markets (this does not include "NEM") |  | Does not go through PJM queue interconnection process and not allowed to inject while in PJM market | WMPA or ISA from PJM queue. | WMPA or ISA from PJM queue. | FERC jurisdictional PJM-run process that resembles the small-unit queue interconnection process
2 | Ability to serve on-site load with generation |  | Yes | None (unless system outage with appropriate switching and, for storage, retail metering) | Yes
3 | Aggregation |  | Generally by EDC, in some cases by LSE or by node | Same electrical location | Same electrical location
4 | Delegation of market relationship: unit owner<> PJM |  | Yes | Yes | Yes
5 | Performance measurement |  | Estimated baseline, except load meter or submeter (where approved) for Reg. | Meter that includes just output of generator | Meter that includes output of generator together with site load
6 | Meter and related hardware requirements |  | Existing retail meter, except where approved for Reg, a PJM-spec submeter. | Dedicated service drop and meter on generator that meets PJM and TO spec | Meter at delivery point that meets PJM and TO spec
7 | Framework for basis of program (participation model)
Instructions:
*Implementation should consider timing for both PJM and stakeholders (added as standard component based on Stakeholder feedback- 2015)
1Design Components - each is an "attibute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Design Component Details" tab (2a).
3. Using informal feedback from the participants, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Option Details" tab 2b.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package", to be documented in tab 3, "Packages Matrix".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.

## 2a. Design Component Details
MIC Special Session on DER
Distributed Resources in PJM Markets
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component | Detailed Description
1 | <enter detailed description of this component>
2 | <enter detailed description of this component>
3 | <enter detailed description of this component>
4 | <enter detailed description of this component>
5 | <enter detailed description of this component>

## 2b. Option Details
MIC Special Session on DER
Distributed Resources in PJM Markets
SOLUTION OPTION DETAILS
Instructions: Complete this form as needed, including more detailed / expansive descriptions of options than the Options Matrix allows.
Cell # | Detailed Description
Corresponding cell number from Options Matrix (ex. 1A, 1B, 2A, etc.) | <enter detailed description of this option>

## 3. Package Matrix
MIC Special Session on DER
Distributed Resources in PJM Markets
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## 3a. Package Details
MIC Special Session on DER
Distributed Resources in PJM Markets
PACKAGE / PROPOSAL DETAILS
Instructions: Complete this form as needed, including more detailed / expansive descriptions of package components than the Package Matrix allows.
Package Solutions2
| A | B | C | D | E
1 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
2 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
3 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
4 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
5 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>

## Parking Lot
MIC Special Session on DER
Distributed Resources in PJM Markets
PARKING LOT
Instructions: Use this space to document any items not specific to another topic area.
Description

## Revision History
MIC Special Session on DER
Distributed Resources in PJM Markets
Revision History
Current Spreadsheet Version:
Instructions: Document all version changes to this matrix for easy identification of changes.
Version | Posting Date | Description of changes
1 | 2016-11-21 | First draft for initial consideration by stakeholders
2 | 2016-12-16 | Second draft after discussion at Dec 16 stakeholder meeting
3