## 24-25 3rd IA Rerun Post
The 24/25 3rd IA rerun based on ER24-1242-000 approved by FERC on 5/6/24.
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Date
2024/2025 | 3rd IA | Auction | Auction window opens | ALL | 2024-05-10
2024/2025 | 3rd IA | Auction | Auction window closes | ALL | 2024-05-16
2024/2025 | 3rd IA | Auction | Auction results posted | PJM | 2024-05-23
Formulas:
Date = +[Date, row above]+6
Date = 7+[Date, row above]

## 25-26 BRA Post
The 25/26 BRA activity dates based on Docket No. ER23-1609-000 approved by the FERC on 6/9/2023 and Docket No. ER24-1242-000 approved on 2/26/24
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Current dates effective as of 2/26/24
2025/2026 | BRA | PSA | Last day for Seller Peak-Shaving Adjustment Plans | PSA | 2023-09-16
2025/2026 | BRA | Planned Generation | Last day for Capacity Market Seller to provide binding offer notification (also known as "notice of intent") for Planned Generation Capacity Resources (contingent upon FERC acceptance of CIFP Docket filed 10/13/23 - er24-99-000) | GEN | 2023-12-12
2025/2026 | BRA | Must Offer | Last day for Capacity Market Sellers to request preliminary must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | N/A
2025/2026 | BRA | MOPR | PJM posts preliminary MOPR screen prices | PJM | 2024-01-14
2025/2026 | BRA | MOPR | Last day for a Capacity Market Seller to certify if subject to State Conditioned Support and/or Buyer Side Market Power | GEN | 2024-01-14
2025/2026 | BRA | Sell Offer Caps | IMM posts preliminary unit specific historical EAS offset | IMM | 2024-01-14
2025/2026 | BRA | Sell Offer Caps | PJM posts gross ACR for seller offer cap | PJM | 2024-01-14
2025/2026 | BRA | PRD | Last day to submit PRD Plan for BRA | PRD | 2024-01-15
2025/2026 | BRA | Winter CIRs | PJM solicits requests for Winter CIRs | PJM | 2024-01-19
2025/2026 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | 2024-01-29
2025/2026 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to request to remove a resource from Capacity Resource status | GEN | 2024-01-29
2025/2026 | BRA | Demand Resource | PJM posts the Zones and sub-Zones, if any, for which end-use customer site-specific information shall be required for DR sell offers under the conditions specified in RAA Schedule 6 subsection A-1(1)(c)(iv). | PJM | 2024-01-29
2025/2026 | BRA | Sell Offer Caps | IMM post final unit specific EAS offset | IMM | 2024-01-29
2025/2026 | BRA | Winter CIRs | Last day for Seller request for Winter CIRs | GEN | 2024-01-29
2025/2026 | BRA | MOPR | PJM/IMM notifies Capacity Market Seller of bases for inquiry and intiation of fact specific review | GEN | 2024-01-29
2025/2026 | BRA | FRR | Last day for first time election of FRR Alternative starting with DY | FRR | 2024-03-18
2025/2026 | BRA | MOPR | Last day for Capacity Market Seller resource-specific MOPR exception request | GEN | 2024-03-19
2025/2026 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to request unit specific sell offer cap price | GEN | 2024-03-19
2025/2026 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for any reason other than the reason specified under OATT Attachment M-Appendix § II.C.4.A (e.g. external sale of capacity, Significant physical operational restriction, ongoing regulatory proceedings related to environmental restrictions and delay in acheiving full commerical operation.) | GEN | 2024-03-19
2025/2026 | BRA | Planning Parameters | Post Planning Parameters | PJM | 2024-04-08
2025/2026 | BRA | MOPR | IMM provides participant with determination on resource-specific MOPR exception request | IMM | 2024-04-18
2025/2026 | BRA | Sell Offer Caps | IMM provides participant with determination of offer cap | IMM | 2024-04-18
2025/2026 | BRA | Must Offer | IMM provides participant with determination on must offer exception | IMM | 2024-04-18
2025/2026 | BRA | Removal of Capacity Status | IMM provides participant with determination on removal of capacity status | IMM | 2024-04-18
2025/2026 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of offer cap | GEN | 2024-04-28
2025/2026 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request for must offer exception | GEN | 2024-04-28
2025/2026 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request to remove a resource from Capacity Resource status | GEN | 2024-04-28
2025/2026 | BRA | MOPR | PJM notifies participant/IMM with determination on resource-specific MOPR exception request | PJM | 2024-05-13
2025/2026 | BRA | Sell Offer Caps | PJM notifies participant/IMM of determination on proposed offer cap | PJM | 2024-05-13
2025/2026 | BRA | Removal of Capacity Status | PJM notifies participant/IMM of its determination on removal of Capacity Resource status | PJM | 2024-05-13
2025/2026 | BRA | Must Offer | PJM notifies participant/IMM of its determination on must offer exception | PJM | 2024-05-13
2025/2026 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM whether it intends to exclude from its Sell Offer some or all capacity from its generation resource on the basis of an identified exception to the RPM Must Offer Obligation | GEN | 2024-05-13
2025/2026 | BRA | FRR | Last day for FRR termination of election ( Last day for election of FRR termination) | FRR | 2024-05-17
2025/2026 | BRA | FRR | Last day for election of FRR Alternative starting with DY | FRR | 2024-05-17
2025/2026 | BRA | MOPR | Participant provides commitment on MOPR price to be used | GEN | 2024-05-18
2025/2026 | BRA | FRR | Last day for Initial/Updated EE M&V Plan for FRR Capacity Plan | FRR | 2024-05-18
2025/2026 | BRA | FRR | Last day for DR Pre-registration Required for FRR Capacity Plan | FRR | 2024-05-18
2025/2026 | BRA | FRR | Last day for DR Plan Template and Officer Certification for FRR Capacity Plan | FRR | 2024-05-29
2025/2026 | BRA | ICTR/QTU | Last day for ICTR/QTU Certification of Increase in Import Capability due | QTU | 2024-06-02
2025/2026 | BRA | Demand Resource | DR Pre-registration Window opens | DR | 2024-06-03
2025/2026 | BRA | FRR | Last day for submission of FRR Capacity Plan due | FRR | 2024-06-17
2025/2026 | BRA | Energy Efficiency | Last day for Initial/Updated EE M&V Plan Due for RPM | EE | 2024-06-17
2025/2026 | BRA | Demand Resource | Last day for DR Sell Offer Plan and Officer Certification Required | DR | 2024-06-17
2025/2026 | BRA | Demand Resource | DR Pre-registration Window closes | DR | 2024-06-17
2025/2026 | BRA | Demand Resource | DR Setup Window opens | DR | 2024-06-18
2025/2026 | BRA | Energy Efficiency | EE Setup Window Opens | EE | 2024-06-18
2025/2026 | BRA | Aggregation | Last day to submit request for aggregate resource | GEN/DR/EE | 2024-07-03
2025/2026 | BRA | Demand Resource | DR Setup Window closes | DR | 2024-07-14
2025/2026 | BRA | Energy Efficiency | EE Setup Window Closes | EE | 2024-07-14
2025/2026 | BRA | Auction | Auction window opens | All | 2024-07-17
2025/2026 | BRA | Auction | Auction window closes | All | 2024-07-23
2025/2026 | BRA | Auction | Auction results posted | PJM | 2024-07-30

## 26-27 BRA Post
The 26/27 BRA activity dates based on Docket No. ER23-1609-000 approved by the FERC on 6/9/2023
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Dates
2026/2027 | BRA | Must Offer | Last day for Capacity Market Sellers to request preliminary must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | N/A
2026/2027 | BRA | PSA | Last day for Seller Peak-Shaving Adjustment Plans | PSA | 2023-09-16
2026/2027 | BRA | Planned Generation | Last day for Capacity Market Seller to provide binding offer notification (also known as "notice of intent") for Planned Generation Capacity Resources | GEN | 2024-06-07
2026/2027 | BRA | MOPR | PJM posts preliminary MOPR screen prices | PJM | 2024-07-07
2026/2027 | BRA | MOPR | Last day for a Capacity Market Seller to certify if subject to State Conditioned Support and/or Buyer Side Market Power | GEN | 2024-07-07
2026/2027 | BRA | Sell Offer Caps | IMM posts preliminary unit specific historical EAS offset | IMM | 2024-07-07
2026/2027 | BRA | Sell Offer Caps | PJM posts gross ACR for seller offer cap | PJM | 2024-07-07
2026/2027 | BRA | Winter CIRs | PJM solicits requests for Winter CIRs | PJM | 2024-07-12
2026/2027 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | 2024-07-22
2026/2027 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to request to remove a resource from Capacity Resource status | GEN | 2024-07-22
2026/2027 | BRA | Demand Resource | PJM posts the Zones and sub-Zones, if any, for which end-use customer site-specific information shall be required for DR sell offers under the conditions specified in RAA Schedule 6 subsection A-1(1)(c)(iv). | PJM | 2024-07-22
2026/2027 | BRA | Sell Offer Caps | IMM post final unit specific EAS offset | IMM | 2024-07-22
2026/2027 | BRA | Winter CIRs | Last day for Seller request for Winter CIRs | GEN | 2024-07-22
2026/2027 | BRA | MOPR | PJM/IMM notifies Capacity Market Seller of bases for inquiry and intiation of fact specific review | GEN | 2024-07-22
2026/2027 | BRA | FRR | Last day for first time election of FRR Alternative starting with DY | FRR | 2024-08-05
2026/2027 | BRA | MOPR | Last day for Capacity Market Seller resource-specific MOPR exception request | GEN | 2024-08-06
2026/2027 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to request unit specific sell offer cap price | GEN | 2024-08-06
2026/2027 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for any reason other than the reason specified under OATT Attachment M-Appendix § II.C.4.A (e.g. external sale of capacity, Significant physical operational restriction, ongoing regulatory proceedings related to environmental restrictions and delay in acheiving full commerical operation.) | GEN | 2024-08-06
2026/2027 | BRA | PRD | Last day to submit PRD Plan for BRA | PRD | 2024-08-09
2026/2027 | BRA | Planning Parameters | Post Planning Parameters | PJM | 2024-08-26
2026/2027 | BRA | MOPR | IMM provides participant with determination on resource-specific MOPR exception request | IMM | 2024-09-05
2026/2027 | BRA | Sell Offer Caps | IMM provides participant with determination of offer cap | IMM | 2024-09-05
2026/2027 | BRA | Must Offer | IMM provides participant with determination on must offer exception | IMM | 2024-09-05
2026/2027 | BRA | Removal of Capacity Status | IMM provides participant with determination on removal of capacity status | IMM | 2024-09-05
2026/2027 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of offer cap | GEN | 2024-09-15
2026/2027 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request for must offer exception | GEN | 2024-09-15
2026/2027 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request to remove a resource from Capacity Resource status | GEN | 2024-09-15
2026/2027 | BRA | MOPR | PJM notifies participant/IMM with determination on resource-specific MOPR exception request | PJM | 2024-09-30
2026/2027 | BRA | Sell Offer Caps | PJM notifies participant/IMM of determination on proposed offer cap | PJM | 2024-09-30
2026/2027 | BRA | Removal of Capacity Status | PJM notifies participant/IMM of its determination on removal of Capacity Resource status | PJM | 2024-09-30
2026/2027 | BRA | Must Offer | PJM notifies participant/IMM of its determination on must offer exception | PJM | 2024-09-30
2026/2027 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM whether it intends to exclude from its Sell Offer some or all capacity from its generation resource on the basis of an identified exception to the RPM Must Offer Obligation | GEN | 2024-09-30
2026/2027 | BRA | FRR | Last day for FRR termination of election ( Last day for election of FRR termination) | FRR | 2024-10-04
2026/2027 | BRA | FRR | Last day for election of FRR Alternative starting with DY | FRR | 2024-10-04
2026/2027 | BRA | MOPR | Participant provides commitment on MOPR price to be used | GEN | 2024-10-05
2026/2027 | BRA | FRR | Last day for Initial/Updated EE M&V Plan for FRR Capacity Plan | FRR | 2024-10-05
2026/2027 | BRA | FRR | Last day for DR Pre-registration Required for FRR Capacity Plan | FRR | 2024-10-05
2026/2027 | BRA | FRR | Last day for DR Plan Template and Officer Certification for FRR Capacity Plan | FRR | 2024-10-16
2026/2027 | BRA | ICTR/QTU | Last day for ICTR/QTU Certification of Increase in Import Capability due | QTU | 2024-10-20
2026/2027 | BRA | Demand Resource | DR Pre-registration Window opens | DR | 2024-10-21
2026/2027 | BRA | FRR | Last day for submission of FRR Capacity Plan due | FRR | 2024-11-04
2026/2027 | BRA | Energy Efficiency | Last day for Initial/Updated EE M&V Plan Due for RPM | EE | 2024-11-04
2026/2027 | BRA | Demand Resource | Last day for DR Sell Offer Plan and Officer Certification Required | DR | 2024-11-04
2026/2027 | BRA | Demand Resource | DR Pre-registration Window closes | DR | 2024-11-04
2026/2027 | BRA | Demand Resource | DR Setup Window opens | DR | 2024-11-05
2026/2027 | BRA | Energy Efficiency | EE Setup Window Opens | EE | 2024-11-05
2026/2027 | BRA | Aggregation | Last day to submit request for aggregate resource | GEN/DR/EE | 2024-11-20
2026/2027 | BRA | Demand Resource | DR Setup Window closes | DR | 2024-12-01
2026/2027 | BRA | Energy Efficiency | EE Setup Window Closes | EE | 2024-12-01
2026/2027 | BRA | Auction | Auction window opens | All | 2024-12-04
2026/2027 | BRA | Auction | Auction window closes | All | 2024-12-10
2026/2027 | BRA | Auction | Auction results posted | PJM | 2024-12-17

## Opening Dates through 2028-2029
Capacity Market Auction Schedule based on Docket No. ER23-1609-000 approved by the FERC on 6/9/2023
Delivery Year | Auction | Approved Schedule
2025/26 | 3rd IA | 2025-02-26
2027/28 | BRA | 2025-06-11
2028/29 | BRA | 2025-12-10
2026/27 | 3rd IA | 2026-02-25
2029/30 | 2029/30 (back on schedule) | 2026-05-20
2027/28 | 2nd IA | 2026-07-15
2027/28 | 3rd IA | 2027-02-24
2028/29 | 2nd IA | 2027-07-14
2029/30 | 1rst IA | 2027-09-15
2028/29 | 3rd IA | 2028-02-23
2029/30 | 2nd IA | 2028-07-19
2029/30 | 3rd IA | 2029-02-21
Notes:
1) Detailed pre-auction activity schedule will be posted ~8 months before above schedule
2) 2029/30 auctions are included for convenience to stakeholders and are not impacted by Docket No ER23-1609-00