## Setup (hidden)
Enter Stakeholder Group Name in cell A2:
Coordination of Long Term Firm Transmission Service Studies
Enter issue title (use title from Issue Tracking if applicable) in cell A5:
Coordination of Long Term Firm Transmission Service Studies

## Workplan
Long Term Firm Transmission Service Task Force
Updated: October 6, 2015
Triennial Review Timing
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC
üVote at MRC
üVote at MC
Multi-Year Pricing Mechanism
üProvide Education
üRefine Interests
üDevelop & Refine Design Components
üDevelop & Refine Component Options
üDevelop & Refine Solution Packages
üBuild Consensus
üFirst Read @ MRC
Vote at MRC
Vote at MC
FERC Filing
OVERVIEW
| Education |  |  | Interests & Design Components | Solution Options & Packages | Narrow packages / Decision making | Tariff Language / Manual Language | Recommendation to PC | PC/MRC Voting
Topic | 2015-06-30 | 2015-07-31 | 2015-08-28 | 2015-10-09 | 2015-10-29 |  | 2015-11-13 | 2015-12-04 | January | February
Charter Development & Approval
Develop Work Plan
Education and Fact-finding | X | X | X | X
Interest Identification |  |  |  | X
Develop Design Components |  |  |  | X
Document Relatative Importance of each component |  |  |  |  | X
Develop Options for each Component |  |  |  |  | X
Narrow Options | [7 empty] | x
Develop Packages | [7 empty] | x
Narrow Packages (Compare Packages to Interests & Importance Ratings) | [7 empty] | x
Consensus Testing | [7 empty] | x
Tier 1/Tier 2 Decision Making | [7 empty] | x
Reporting | [7 empty] | x

## 1. Interest Identification
Long Term Firm Transmission Service Task Force
Interest Identification
Instructions: List interests of all parties on this page.
1 | Energy from External resources participating in PJM market are able to be delivered reliably
2 | Modify Long Term Firm Transmission studies to provide results consistent with Capacity Import Limit studies
3 | Ensure all new testing requirements are incorporated in future baseline and new service queue evaluations
4 | All internal and external long term firm transfer commitments are treated equally
5 | Addressing concerns in relation to netting the transmission service along the seam.
6 | Ensuring deliverability testing methodology is consistent with the type of service requested (Generation Deliverability testing)
7 | Ensure the study process captures the seasonal aspects of the system
8
9
10
11
12
13
14
15

## 2. Options Matrix- Design Comp.
Long Term Firm Transmission Service Task Force
OPTIONS MATRIX
Strive for simplicity
Solution Options2
# | Design Components1 | Priority | Status Quo | A | B | C | D | E
1 | Modeling |  | I. Net imports and exports II. CBM not modeled III. Reservations not explicitly modeled in base case | I. Base case a. Model reservations explicitly (individual generator(s) as applicable) b. Model imports at 100% c. Model exports at percentage based on utilization (currently 65%) and ramp to 100% for testing - This utilization percentage shall be updated periodically by PJM to be implemented in the base case studies for any study year. Additionally, ensure that the utilization percentage is no less than the sum of all export reservations associated with an external firm commitment d. Model CBM at each seam based on percentages determined during initial base case development II. Queue studies a. Model all existing service as above (service which had been modeled for the base case development & studies) b. Model all queue requests at 100% (import and export) to determine individual impacts c. Model CBM
2 | Thresholds |  | <500kV then: 5% dfax or 5% rating >500kV then: 10% dfax or 5% rating | Import studies All voltages: 3% dfax or 3% rating Export studies All voltages: 3% dfax or 3% rating for external facilities Employ existing thresholds for internal facilities
3 | Study methods |  | Generation deliverability, common mode outage testing | Incorporate the new case modeling and thresholds, otherwise no changes
4 | CIL studies |  | Not incorporated for LTF studies in queue | Incorporate provisions to test/upgrade CIL impacted facilities
5 | [8 empty] | Low
6 | [8 empty] | Low - Medium
7 | [8 empty] | Low - High
8 | [8 empty] | Medium
9 | [8 empty] | Medium - High
10 | [8 empty] | High
11
12
Instructions:
1Design Components - each is an "attribute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Component Details" tab.
3. Using informal/non-binding voting, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Solution Details" tab.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.
7. If consensus is achieved on a single package (Tier 1 decision-making method), this will be documented in a Consensus Proposal Report to the parent committee.
8. If not, the group will identify up to 3 possible solution packages in a comparative Proposal Alternatives Report to the parent committee (Tier 2 decision-making method).

## 2a. Component Details
Long Term Firm Transmission Service Task Force
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component |  | Detailed Description
1 |  | <enter detailed description of this component>
2 |  | <enter detailed description of this component>
3 |  | <enter detailed description of this component>
4 |  | <enter detailed description of this component>
5 |  | <enter detailed description of this component>

## 2b. Solution Details
Long Term Firm Transmission Service Task Force
SOLUTION DETAILS
Instructions: Complete this form as needed. Potential solutions should be populated from the Proposal Matrix
Package Solutions2
| A | B | C | D | E
1
2
3
4
5

## 3. Package Matrix
Long Term Firm Transmission Service Task Force
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## 4. Parking Lot
Long Term Firm Transmission Service Task Force
Interest Identification
Instructions: Use this space to document any items not specific to another topic area.
Item # | Description | Response
1
2
3
4
5
6
7
8

## Revision History
Long Term Firm Transmission Service Task Force
Revision History
Current Spreadsheet Version:
Version | Posting Date | Description of changes
1 | 2015-10-06 | Original
2
3