## Setup
Enter Stakeholder Group Name in cell A2:
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Enter issue title (use title from Issue Tracking if applicable) in cell A5:
Seasonal Capacity Resources

## Workplan
2016-17 Seasonal Capacity Resources Senior Task Force (SCRSTF) Work Plan
Updated: March 17, 2016
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC | [5 empty] | 2012-11-29
üVote at MRC | [6 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  |  | 2013-03-01: 2013-03-01
Issue | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013 | April | May | June | July | August | September | October | November | December | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01
Seasonal Resources Problem Statement | [10 empty] | July: Package development; August: Package narrowing and polling; September: SCRSTF Voting MRC 1st Read; October: MRC Voting MC Voting; November: PJM FERC Filing | FERC Decision | BRA Planning Parameters Posted |  |  | 2020/2021 BRA
[11 empty] | April: SCRSTF Stakeholder Process; October: Parent Committee and FERC Process |  | RPM Deadlines
Updated: March 17, 2016
Detailed Work Plan | 6.26 | 7.17 | 7.31 | 8.9 | 8.26 | 8.28 | 9.9 | 9.18 | 9.24 | 9.26 (MRC) | 2016-04-04 | 2016-04-18 | 2016-04-26 | 2016-05-06 | 2016-05-25 | 2016-06-06 | 2016-06-21 | 2016-07-11 | 2016-07-26 | 2016-08-12 | 2016-08-22 | Sept | Oct | Nov
Create Charter |  | x | x | x |  | x | x | bar: 2016-04-04 to 2016-05-06
Provide Education |  |  | x | bar: 2016-04-04 to 2016-05-25
Document Interests |  |  |  | x |  | x | x | bar: 2016-04-26 to 2016-05-06
Develop & Refine Design Components | [5 empty] | x | x |  | x | bar: 2016-05-06 to 2016-05-25
Develop & Refine Component Options | bar: 2016-06-06 to 2016-07-11
Develop & Refine Solution Packages | bar: 2016-07-11 to 2016-08-22
Build Consensus | bar: 2016-08-12 to 2016-08-22
SCRSTF Vote | [21 empty] | x | bar: 2016-08-22
First Read @ MRC | [21 empty] | x
Vote at MRC | [22 empty] | x
Vote at MC | [22 empty] | x
FERC Filing | [23 empty] | x

## 1. Interest Identification
Seasonal Capacity Resources Senior Task Force (SCRSTF) |  | Updated: May 6, 2016
Seasonal Capacity Resources
Interest Identification
Instructions: List interests of all parties on this page.
Manual 34, Documenting Interests: "the purpose of this step is to ensure that all stakeholders have a common understanding of each other’s interests vis-à-vis their potential positions on individual issues (interests and positions are different – positions are assertions about what people say they want, while interests are why people want what they want (needs, motivations, concerns, and desires behind the position".
| Individual Interests | Interest "Buckets" | Overarching Interests
1 | Maintain 100% Capacity Performance procurement for Delivery Years 2020/2021 and beyond. Ensure capacity resources are obligated to respond to emergency conditions throughout the year | Broad RPM Design Features
6 | Maintain single capacity product with clear transparent market rules and administratively feasible and repeatable RPM auction clearing process Establish uniform compensation, performance and other requirements across all capacity resources.
21 | Recognize the value of reliability contributions of resources that may not be available as CP
5 | Avoid seasonal markets as previously discussed and abandoned in 2006 and in 2011. Avoid solutions that introduce complexity without adding commensurate reliability benefits.
18 | Right size customers' capacity purchase obligation given PJM's summer-peaking system
15 | Ensure that markets do not over-procure resources by accurately accounting for and valuing supply- and demand-side resources that, by themselves, inherently cannot qualify as Capacity Performance, but nevertheless contribute to installed capacity.
2 | Avoid relaxation of 1-in-10 reliability standard as is done today to accommodate sub-annual capacity product types. | Resource Adequacy/Reliability Planning Parameters | Ensure RPM meets 1-in-10 reliability standard without overprocuring resources
12 | Ensure the capacity performance rules do not lead to an over-procurement of resources necessary to meet the reliability needs of the system
37 | Avoid changes to IRM calculations and CETO/CETL determination
3 | Ensure robust Measurement and Verification methods in place for all capacity resources | Demand Response M&V | Ensure Demand Response measurement and verification is robust, and reflects resource adequacy planning principles
9 | Establish measurement and verification of capacity performance demand resources consistent with the definition of capacity as a planning tool
4 | Must meet the comparability standards of not being unduly discriminatory or preferential | Comparable Treatment of Capacity Resources | Ensure Capacity Resources of all types have comparable, but not necessarily equal, requirements which respect inherent differences in resource types
10 | Preserve comparable treatment for all capacity resources while not requiring identical treatment
44 | Ensure performance obligations are comparable for aggregated seasonal resources when compared to traditional generation resources
40 | Recognize that different capacity resources may have different responses
43 | Ensure that aggregated resource capacity is operated and offered in a way that is no less flexible than its true capabilities.
39 | Maintain a capacity market price signal that properly incentivizes new entry and properly compensates resources meeting CP obligations | Price Signal | Ensure RPM provides a price signal that incetivizes new entry and properly values resources of all types
11 | Ensure proper valuation of all capacity resources in order for proper price signals to be sent
29 | Set prices for seasonal resources in a manner consistent with RPM clearing mechanisms
33 | If any potential barriers for renewable entry participation into the capacity market (as a full participant) are identified, these barriers should be adequately addressed | Recognizing seasonal resources in the capacity market
7 | Investigate roadblocks in the current Resource Aggregation mechanism for seasonal resources Ensure that the rules for resource aggregation do not contain unnecessary roadblocks or barriers.
13 | Establish a framework for incorporating seasonal resources in the capacity market that will be sustainable and facilitate the incorporation of new technologies and innovation
16 | Recognize that capacity needs vary over the year and that seasonal resources can help meet seasonal variations
25 | Identify potential seasonal and other opportunities for increased participation of customers in PJM energy, ancillary, and capacity markets through growth in undeveloped resources, e.g., thermal storage such as grid interactive water heaters, ice, silica alternatives.
30 | Base any limits on seasonal resources on reliability analysis
31 | Ensure clearing of seasonal resources in constrained zones does not overstate deliverability limits
32 | Minimize the MW amount of renewable energy resources that are precluded from capacity market participation as a result of PJM's annual construct
34 | Use existing proven resources in seasons when available
35 | Consider historical energy performance to assess seasonal value (e.g. wind in January 2014)
8 | Preserve ability of the PJM capacity market to capture the maximum amount of summer only resources reasonably possible to reliably run the system in accordance with the terms of the “saturation analysis” previously adopted by PJM.
22 | Find tools for demand response to help serve as a demand-side check on capacity prices | Demand Response | Ensure Demand Response participation, either through RPM or outside RPM, is a viable option for customers to contribute to reliability and to reduce capacity obligations/costs
24 | Distinguish potential solution alternatives between demand response opportunities for larger customers versus smaller (i.e. mass market customers).
26 | Individual customers that maintain loads below their PLC should be fully credited for such reduction
36 | Ensure the continued ability for demand (load) to respond dynamically, optimally and efficiently to supply bids in BRA auctions
19 | Find ways to allow customers to utilize their interruptible capability to assist in PJM reliable operations and to help offset their own capacity costs
20 | Recognize the value of reliability contributions of resources with interruptibility
28 | Preserve ability of summer-only demand resources, including residential A/C programs, to participate as stand-alone capacity resources
42 | That the group will seriously investigate solution options outside RPM
38 | Evaluate demand side alternatives to include seasonal/limited resources in RPM with 100% CP
27 | Individual customers should be able to manage their performance risk for all hours of a winter day
14 | Preserve ability of PJM markets to continue to capture the full amount of summer available resources that have been and are currently being relied upon to meet system needs.
23 | Evaluate and compare the cost impacts to customers of potential solution alternatives to the cost impacts to customers of the status quo. | Cost Impacts
41 | Interest in providing a market for resources that will help address Clean Power Plan requirements | Public Policy
17 | Avoid procuring long-lasting infrastructure that will contribute to future stranded costs by appropriately considering public policy objectives and trends and adapting the resource procurement process accordingly

## 2. Options Matrix- Design Comp.
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
OPTIONS MATRIX
Solution Options2
# | Design Components1 | Priority | Status Quo | A | B | C | D | E
* | Implementation
1
2
3
4
5 | [8 empty] | Low
6 | [8 empty] | Low - Medium
7 | [8 empty] | Low - High
8 | [8 empty] | Medium
9 | [8 empty] | Medium - High
10 | [8 empty] | High
11
12
Instructions:
*Implementation should consider timing for both PJM and stakeholders (added as standard component based on Stakeholder feedback- 2015)
1Design Components - each is an "attibute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Design Component Details" tab (2a).
3. Using informal feedback from the participants, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Option Details" tab 2b.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package", to be documented in tab 3, "Packages Matrix".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.

## 2a. Design Component Details
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component | Detailed Description
1 | <enter detailed description of this component>
2 | <enter detailed description of this component>
3 | <enter detailed description of this component>
4 | <enter detailed description of this component>
5 | <enter detailed description of this component>

## 2b. Option Details
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
SOLUTION OPTION DETAILS
Instructions: Complete this form as needed, including more detailed / expansive descriptions of options than the Options Matrix allows.
Cell # | Detailed Description
Corresponding cell number from Options Matrix (ex. 1A, 1B, 2A, etc.) | <enter detailed description of this option>

## 3. Package Matrix
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## 3a. Package Details
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
PACKAGE / PROPOSAL DETAILS
Instructions: Complete this form as needed, including more detailed / expansive descriptions of package components than the Package Matrix allows.
Package Solutions2
| A | B | C | D | E
1 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
2 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
3 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
4 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>
5 | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component> | <enter detailed description of this component>

## Parking Lot
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
PARKING LOT
Instructions: Use this space to document any items not specific to another topic area.
Date | Description | Process | Addressed? Y/N | Requestor
2016-03-28 | Overlap of intermittent resources capacity injection rights discussion at PC / winter deliverabilty analysis (CETO/CETL) | Education; Stakeholder process alignment |  | Mike Jacobs, UCS
2016-04-04 | Demand Response Winter M&V Examples: 1. Customer load shaped like system load (winter) 2. Illustrative industrial customer load that maintains level demand for an 8 hour workday but can curtail to 25% of normal peak. (winter) 3. Load that has winter peak demand equal to FSL, FSL at 25% of PLC. Assume that Summer capability is PLC minus PSL. | Education | Y, 4/23 meeting and 5/25 | Bruce Campbell, Energy Connect
2016-04-18 | Compare time allotted for DR aggregation, registration and offers in CP transition auctions with time allotted in prospective auctions | Education |  | Jason Barker, Exelon

## Revision History
Seasonal Capacity Resources Senior Task Force (SCRSTF)
Seasonal Capacity Resources
Revision History
Current Spreadsheet Version:
Instructions: Document all version changes to this matrix for easy identification of changes.
Version | Posting Date | Description of changes
1
2
3