## Key System Upgrades 2019_2020
System Upgrades With Potential Impact to Congestion June 2019 Through May 2020
Description | TO | Projected In-service Date
New Skiffes Creek - Whealton 230 kV line | Dominion | 2018-12-30
Cut-in of line 93505 Tazewell - Kendall 345 kV line into Dresden | ComEd | 2019-01-23
Reconductor the Falls - U.S. Steel 138 kV line | PECO | 2019-03-31
New Orchard - Cardiff 230 kV line (remove, rebuild and reconfigure existing 138 kV line) and associated substation upgrades, environmental work | AEC | 2019-05-15
Surry to Skiffes Creek 500 kV Line (7 miles overhead) | Dominion | 2019-05-30
Skiffes Creek 500-230 kV Tx and Switching Station | Dominion | 2019-05-30
Construct a second 138 kV line between West Fremont and Hayes substation on open tower position of the West Fremont - Groton - Hayes 138 kV line | ATSI | 2019-06-01
Reconductor Northwest - Northwest #2 115kV 110574 substation tie circuit with 2167 ACSR to achieve ratings of 400/462 MVA SN/SE | BGE | 2019-06-01
Upgrade conductor ratings of Cordova - Nelson, Quad Cities - ESS H-471 and ESS H-471 - Nelson 345 kV lines and mitigating sag limitations | ComEd | 2019-06-01
Rebuild the Cunningham - Dooms 500 kV line | Dominion | 2019-06-01
Increase ratings of Peach Bottom 500/230 kV transformer to 1479 MVA normal/1839 MVA emergency | PECO | 2019-06-01
Upgrade the Riverside 115kV substation strain bus conductors on circuits 115012 and 115011 with double bundled 1272 ACSR to achieve ratings of 491/577 MVA SN/SE on both transformer leads | BGE | 2019-07-31
Rebuild existing East Coshocton - North Coshocton double circuit line which contains Newcomerstown - N. Coshocton 34.5 kV Circuit and Coshocton - North Coshocton 69 kV circuit | AEP | 2019-08-26
Perform a Sag Study of Nagel - West Kingsport 138 kV line to increase the thermal rating of the line | AEP | 2019-09-30
Rebuild existing 69 kV line as double circuit from George Washington - Dilles Bottom 138 kV. One circuit will cut into Dilles Bottom 138 kV initially and the other will go past with future plans to cut in. | AEP | 2019-11-01
Reconductor limiting span of Lallendorf - Monroe 345kV (crossing of Maumee river) | ATSI | 2019-11-01
Install second 230/69 kV transformer at Cedar Grove | PSEG | 2019-11-01
Build a new 69 kV circuit from Cedar Grove to Great Notch | PSEG | 2019-11-01
Optimal Capacitors Configuration: New 175 MVAR 230 kV capacitor bank at Brambleton substation, new 175 MVAR 230 kV capacitor bank at Ashburn substation, new 300 MVAR 230 kV capacitor bank at Shelhorn substation, new 150 MVAR 230 kV capacitor bank at Liberty substation. | Dominion | 2019-12-01
Rebuild Everetts - Leggetts 115kV Line #82 Crossroads DP (19.1 miles) to current standards with a summer emergency rating of 353 MVA at 115kV | Dominion | 2019-12-30
Replace terminal equipment at AEP's Danville and East Danville substations to improve thermal capacity of Danville - East Danville 138 kV circuit | AEP | 2019-12-31
Double capacity for 6 wire Burger-Cloverdale No. 2 138 kV line and connect at Holloway and Point A | ATSI | 2020-03-01
Reconductor the Emilie - Falls 138 kV line, and and replace station cable and relay | PECO | 2020-03-31
Construct a new 500-138 kV substation as a 4-breaker ring bus with expansion plans for double-breaker-double-bus on the 500 kV bus and breaker-and-a-half on the 138 kV bus to provide EHV source to the Marcellus shale load growth area. Projected load growth of additional 160 MVA to current plan of 280 MVA, for a total load of 440 MVA served from Waldo Run substation. Replace primary relaying and carrier sets on Belmont and Harrison 500 kV Remote End Substations. Construct additional 3-breaker string at Waldo Run 138 kV bus. Relocate the Sherwood #2 line terminal to the new string. Construct two single circuit Flint Run - Waldo Run 138 kV lines using 795 ACSR (approximately 3 miles). After terminal relocation on new 3-breaker string at Waldo Run, terminate new Flint Run 138 kV lines onto the two open terminals. | APS | 2020-05-14
Reconductor the North Meshoppen - Oxbow - Lackawanna 230 kV circuit and upgrade terminal equipment (PENELEC portion) | PENELEC | 2020-05-15
Highlighted upgrades will be modeled as in-service in annual ARR allocation and annual FTR auction
Note: See the RTEP Construction Status page of the PJM web site for a complete list of all planned RTEP upgrades including up-to-date projection of in-service date